| Housing Program |  | PO Box 173580 Bozeman, MT 59717-3580 Phone 406-994-3451 Fax 1406 994 5417 |
| --- | --- | --- |

Evaluation Report

State of Montana 
Residential Energy Assistance CHallenge (REACH) Program

(Grant Number 2000 G992206)

Christopher Mee
Weatherization Technical Specialist
Lead Evaluator

Michael P. Vogel Ed.D., Professor
Housing and Environmental Quality Specialist
Evaluation Director

TABLE OF CONTENTS

TABLE OF CONTENTS	2

Executive Summary	3

I.  Project Overview and Implementation	7

II. Description of Target Population, Analysis of Need, Project Assumptions	9

III.  Project Design Framework: Interventions, Outcomes and Goals	13

Intervention	13

Immediate Changes/Outcomes	14

Intermediate Changes/Outcomes	15

Achievement of Overall Project Goals	16

Work Plan	17

Program Logic Model	18

Program Changes and Modifications	21

IV. Evaluation Methodology	21

V. Process Evaluation Findings	23

VI. Outcome Evaluation Findings	30

VII. Client Survey	35

Appendix	41

# Executive Summary

Overview

The Montana Residential Energy Assistance CHallenge (REACH) program is a federally funded residential energy assistance demonstration program, which provided an array of services and benefits to clients who are recipients of the Low-Income Home Energy Assistance Program (LIHEAP) in the State of Montana.  REACH services and benefits included a client education questionnaire, diagnostic testing and inspection of combustion heating devices, a heating system retrofit analysis, a propane tank purchase analysis,  an inspection to identify necessary energy related health and safety and minor home repairs and assess the need for smoke and carbon monoxide detectors. During the past three years (December 31, 2000 -December 31, 2002) the Montana Department of Public Health and Human Services Intergovernmental Human Services Bureau implemented the program in thirty-one Montana counties served by four Human Resource Development Councils (HRDC’s). This report is a comprehensive review and evaluation of the program during this period.

REACH Goals

Montana's REACH Program was designed to ensure that participants have the resources to live in dignity and health by:

- Ensuring their energy burden not greater as a percentage of annual income than the average for all Montanans (4.1%)

- Ensuring their homes are free of energy related health and safety hazards

- Encouraging landlords and fuel vendors to participate in activities to enhance participants’ ability to make timely payments

- Improving participants’ ability to regularly pay energy cost

- Eliminating homelessness due to high energy costs and the presence of energy related health and safety hazards

- Providing participants, especially welfare reform recipients, more disposable income to satisfy basic needs necessary to achieve self-sufficiency

- Protecting existing energy conservation measures eliminating the need for future investment

The money saved by recipients of the REACH program through energy savings can be used for other family necessities.  By having the opportunity to utilize energy more efficiently and cost effectively, the people in these areas have achieved one of the primary goals of the REACH program… adequate, safe and well heated households.

Program Intervention

The Montana REACH Program performed an initial needs assessment and inspection on each dwelling by a certified energy auditor to determine whether there were opportunities to provide health and safety measures and perform cost-effective energy conservation related home repairs. The scope of the inspection included examination of the dwelling envelope and an assessment of existing carbon monoxide and smoke detectors on all dwellings.  A client education questionnaire, diagnostic testing and inspection of combustion heating devices, a heating system retrofit analysis, and an inspection to identify necessary energy related health and safety and minor home repairs were also included.

While performing retrofits and repairs of combustion heating devices, mercury thermostats were replaced with non-mercury thermostats.  The mercury thermostats were returned (at no cost to the REACH Program) to the manufacturers participating in the Mercury Thermostat Reduction and Recycling Program, which is sponsored by the Thermostat Recycling Corporation as a means of reducing mercury levels in landfills.  Where appropriate programmable “night set-back” thermostats were installed.

Evaluation Methodology

An important component of the Montana REACH Program is the evaluation of the activities carried out with REACH funds and their efficacy to achieve stated goals related to reducing participant home energy costs and increasing the ability of participants to meet such costs independent of payment subsidies.

The process evaluation conducted by MSU documents and describes all aspects of development and implementation of the proposed Program.  The process evaluation can serve as a document to assist in replication of program activities by other Federally funded LIHEAP programs.

The outcome evaluation conducted by MSU is intended to document and interpret the results of program activities relative to expected goals and performance outcomes and to assess whether program activities can be replicated with similar results by other Federally funded LIHEAP programs.  In addition the evaluation addresses performance with respect to gathering data and analyzing the net affects attributable to program activities/interventions.

REACH Clients

The average Montanan spends 4.1 percent of household income on heating costs.  The Montana REACH program design was based on the fact that 71.1 percent of low-income households spend more than 4.1 percent of their household income on heating costs.

The target population served by the proposed REACH program was LIHEAP client households with the highest home energy needs.  The energy needs of LIHEAP households in each HRDC’s areas were calculated by multiplying the energy burdens of households occupied by elderly, disabled and Montana’s welfare reform program (FAIM) recipients by 1.25.  The energy needs of all other LIHEAP households remained the same as their respective energy burdens.  In the case of the elderly and disabled, the formula gave priority to those in this client population who were the most at risk in an energy crisis.

Households that included recipients of Montana’s welfare reform program were also at risk as their Temporary Assistance to Needy Families (TANF) benefits expired.  This preference includes Montana’s families with young children that are most in need.  Applying these factors, the REACH program focused on those Montana households most vulnerable to rising energy costs.  Participants in the Montana REACH Program were selected from LIHEAP recipient households that had an arrearage of at least 1/2 of the annual LIHEAP payment.  In many cases the energy cost burden for these households was greater than 15% of the total household income. In addition, participants were chosen if their dwelling structure or heating equipment represented a potential health or safety risk or they appeared to be highly motivated to participate in the program.

The Montana REACH Program completed a total of 568 households during the program period. The energy burden portion of the evaluation focused on the program’s impact on a representative sample of 72 of these participants who occupied regulated electric and natural gas-heated households. They included occupants with an average age of 59.75 years old. The mean annual income across all agencies and participants was $9,812.11.  The mean number of occupants per REACH participant household was 2.75.

Client Survey Results

At the conclusion of the Montana REACH program, participants were asked to complete a questionnaire about their REACH experience. The overwhelming consensus of 126 participants that returned their survey was that the REACH program was extremely beneficial to them and to their families. The participant’s comments reflect the many ways in which the Montana REACH program has had a positive impact on their household environment and their ability to better manage their energy resources.

These outcomes are most clearly shown by the following findings:

1.	Approximately 53% of the participants that responded indicated that after receiving REACH/Weatherization services in their home they were able to pay their energy bill in full every month  all of the time.  30% indicated they were now able to pay their energy bill most of the time.  This is very significant since only 20% of the clients that responded indicated they could always pay their bill on time before participating in REACH.

2.	Approximately 63% of the participants reported that after receiving REACH/Weatherization services they no longer worried about having to leave their home because of energy related health and safety issues and 21% responded they rarely worried.  This too is significant because before REACH 15% reported they often worried about this issue and 26% worried some of the time about this issue.

3.  Approximately 72% of the REACH participants expressed through the survey, that as a result of their homes receiving REACH/Weatherization services they were more comfortable and livable than before the services were installed.

4.  REACH participants that were propane costumers were asked a specific question about the ability to purchase lower cost propane as a result of owning their own tank and if it affected there fuel cost for the year.  Approximately 50% of the participants that responded indicated that this affected their fuel cost more than they expected and 77% of the participants that responded felt their energy bills had decreased as a result of being able to purchase lower cost propane.

Summary Conclusion

In summary, these findings indicate that the Montana REACH Program was able to assist clients through education, energy conservation measures and making available the opportunity to acquire services not readily available through other low-income services provided by the HRDC’s.  The success of the Montana REACH program in achieving its objectives provides strong support for continued activities of coordinated services and educational resources which has been proven to be an effective approach in reducing the consumption and costs of energy for low-income households. This also confirms the value of lowering low income households’ high-energy burden.  The evidence presented in this report indicates clearly that the Montana REACH program has greatly assisted low-income households ensuring participants have the resources to live in dignity and health.

# I.  Program Overview and Implementation

Grantee and Sub-grantee Information

Montana’s Weatherization Assistance Program (WAP) and the Low Income Home Energy Assistance Program (LIHEAP) are situated in the Human Resource Development Council (HRDC) Services Section of the Intergovernmental Human Services Bureau, which is part of the Human and Community Services Division. The Human and Community Services Division is one of nine divisions within the Montana Department of Public Health and Human Services.

The Intergovernmental Human Service Bureau (IHSB) contracted REACH funds to 4 of the 10 HRDC’s, and provided program oversight, training, technical assistance and monitoring.  Jim Nolan, Chief of IHSB, has worked in his capacity since the beginning of LIHEAP. He is responsible for planning, establishing and overseeing all goals, objectives and operations of the State of Montana’s efforts in the following areas: Weatherization, LIHEAP, Community Services Block Grant, Emergency Shelter Grant program, Emergency Community Services for the Homeless program, and Commodities program. The REACH Program Coordinator for the State is Kane Quenemoen.  Mr. Quenemoen is Section Supervisor for Montana’s LIHEAP, CSBG and Weatherization programs.

Executive Leadership

The executive leadership for all HRDC's is their Executive Director who was hired by the respective Board of Directors.  The Executive Directors had oversight responsibilities for the REACH program.

Action for Eastern Montana (AEM) in Glendive has provided energy conservation programs for over 22 years in seventeen (17) counties (Carter, Custer, Daniels, Dawson, Fallon, Garfield, McCone, Phillips, Prairie, Powder River, Richland, Roosevelt, Rosebud, Sheridan, Treasure, Valley, and Wibaux) in eastern Montana.  Leslie Colbrese, AEM Executive Director, was responsible for managing and administering the REACH Program for AEM.

District IV HRDC in Havre has been providing energy conservation programs for over 20 years in 3 counties (Blaine, Hill, and Liberty) in north central Montana.  Thomas Bolan, District VI HRDC Executive Director, was responsible for the overall management of operations of the REACH Program.

District VI HRDC in Lewistown has been providing energy conservation programs for the past 20 years in 6 counties (Fergus, Golden Valley, Judith Basin, Musselshell, Petroleum, and Wheatland).  Pam Higgins, District VI HRDC Executive Director, had general oversight responsibilities for this program.

District VII HRDC in Billings has been providing energy conservation programs for over 20 years in 5 counties (Big Horn, Carbon, Stillwater, Sweet Grass, and Yellowstone).  Carl Visser, District VII HRDC Executive Director, was responsible for the overall management of operations for the REACH program for the agency.

Program Priority

The Residential Energy Assistance CHallenge  (REACH) Program was a priority program operated within the energy divisions of the HRDC’s.  This program empowered the customers of the area toward self-sufficiency by permanently reducing their energy costs, and enhancing their ability to make regular utility payments.  This program placed a priority on educating customers and on health and safety issues in the dwellings they occupied.

Staff Resources and Responsibilities

In the designation of the Community Base Organization (CBO) Recipients for the REACH program, priority was given, as required by the authorizing legislation, to eligible entities (described in Section 673 of the Community Services Block Grant Act - amended), which have a record of successfully providing service under LIHEAP and which receive funds from the Department of Energy’s Weatherization Assistance Program.  District VI Human Resource Development Council, District VII Human Resource Development Council, District IV Human Resource Development Council and Action for Eastern Montana all have a record of successfully providing LIHEAP and receive funding to operate the Department of Energy’s Weatherization Assistance program through the leadership of the following program Directors:

- Gary Witsoe, AEM Weatherization Program Director, was the organization’s REACH Program Director.

- Camie Jorgensen, District IV HRDC Energy Programs Director, was the agency’s REACH Program Director.

- Glenn Richards, District VI HRDC, was the REACH Program Director.

- Wayne Schmidt, District VII HRDC Energy Specialist, was the Agency’s REACH Program Director.

II. Description of Target Population, Analysis of Need, Program Assumptions

Needs of the Client Population to Be Served

The average Montanan spends 4.1 percent of household income on heating costs.  The Montana REACH program design was based on the observation that 71.1 percent of low-income LIHEAP households spend more than 4.1 percent of their household income on heating costs.    The target populations actually served by the REACH program included client households with the highest home energy needs.  The energy needs of households occupied by elderly, disabled and Montana’s welfare reform program (FAIM) recipients in each CBO’s area were calculated by multiplying the energy burdens of households by 1.25.  The energy needs of all other households were the same as their respective energy burdens.  In the case of the elderly and disabled, this formula gave priority to those in this client population who were at the most risk for an energy crisis.  Those households who were recipients of Montana’s welfare reform program were also at risk as their Temporary Assistance to Needy Families (TANF) benefit time clocks expired.  This preference includes Montana’s families with young children with the most need.  In using these factors, the REACH program focused on those Montana LIHEAP households most vulnerable to an energy crisis.

Current Services Available

The Department of Energy and Oil Overcharge Weatherization programs provided energy conservation measures to approximately ten (10) percent of the LIHEAP households in the target service areas.  Measures performed under these programs include attic insulation, floor insulation, wall insulation, crawl space insulation, infiltration reduction materials, and heating system repairs.  Approximately 1.6 percent of the area’s households receive Weatherization assistance each year through Montana Power Company’s (now NorthWestern Energy) (MPC/NWE) weatherization program.  In addition to the measures described above, the MPC/NWE program provides heating system retrofits in instances where switching to an alternate fuel source is cost effective.  Effective January 1, 1999, electric cooperatives and regulated utilities in the proposed service area were required to expend a minimum of .408 percent of their 1995 gross operating revenues for low-income energy assistance activities.  Co-funding REACH program heating system retrofits provided them a vehicle to meet their respective Uniform Systems Benefit Charge (USBC) obligations.

Where and How Current Services Fail To Meet Needs

Current services, which are provided to only approximately 10 percent of LIHEAP households each year, failed to meet clients’ needs in terms of providing more efficient heat sources because the DOE weatherization program does not allow heating system retrofits except for health and safety concerns.  Moreover, the weatherization program under funded minor home repairs and did not include household specific energy education, the purchase of fuel oil and propane tanks, or the routine installation of programmable thermostats, carbon monoxide and smoke detectors. Weatherization program managers in the program area estimated that approximately fifty-seven (57) percent of the LIHEAP homes are at risk for health and safety problems because of an ill maintained, aging or inadequate heating system.  Other than the MPC/NWE program, which served only a small fraction of LIHEAP customers in the target area, utility companies and fuel vendors offered no energy conservation services comparable to those in either the weatherization or in the REACH program.

Why the Services Were Appropriate and Meet These Needs

The services provided by REACH allowed for a heating system retrofit analysis to be conducted in each selected household.  In the original 325 homes identified before REACH services were implemented, recipients benefited from fuel switching and increased household energy efficiency there by significantly lowered out-of-pocket home heating costs.  Minor home repairs were introduced to protect energy conservation measures and reduce or eliminate the need for costly future replacements.  Provision of heating system repairs, carbon monoxide and smoke detectors brought low-income households into compliance with building codes applicable to new construction. As part of the REACH program approximately 275 existing heating systems, where heating system retrofits were not cost-effective, were to be inspected, tested, cleaned and repaired.  These services, coupled with LIHEAP heating assistance benefits, ensured a safe living environment and reduced the energy burdens of Montana’s neediest households to approximate the average energy burdens of all Montana households.

Target Population and Geographic Area that was served

The target population for the Montana REACH program included those households with the highest energy needs. From the outset of the program, there were 4,260 LIHEAP households in the geographic area included in the original proposal.

The initial energy burden was represented as an average household energy expenditure ($942) as a percent of average household income ($22,988), 4.1 percent of income.  The program considered the elevated number of heating degree-days in the program area.  The Montana DOE Weatherization Program adopted a savings to investment ratio of 1.8 in order to stay within DOE’s allowable average cost per home of $2,032.  In contrast, warmer climate states are able to use a savings to investment ratio of 1.0 and still meet DOE’s average cost per home requirement.

The geographic area impacted included 31 of Montana’s 56 counties or approximately one-half of the state’s geographic area.  The area also encompasses the Rocky Boy, Fort Peck, Fort Belknap, Northern Cheyenne and Crow Indian Reservations.  The appropriate CBOs served all residents of the Crow reservation and non-tribal residents of the Rocky Boy, Fort Belknap, Fort Peck and Northern Cheyenne reservations.

Building Type, Condition and Age of Low-Income Housing

Eastern Montana has not experienced the recent “boom” in population seen in the western half of the state and new housing starts are relatively low.  Census data showed that approximately one third of the housing stock in Eastern Montana’s rural areas was constructed before 1950.  In almost half of the counties in the program area, the percentage of homes built before 1950 is 40 percent or higher.  Survey data indicated that this is the housing stock low-income families can afford to occupy. These families are not able to maintain or upgrade these homes and therefore their condition deteriorates and is typically substandard.

Predominant Fuel Used for Home Heating

The predominant fuel used by LIHEAP clients for home heating is natural gas.  However, this program targeted those households using electric, propane, oil, and other more costly sources of fuel. Fifteen percent or 618 LIHEAP households in the program area served use propane heat. In the geographic area to be served, the total amount paid in 1998 LIHEAP benefits for propane was as follows:

- $89,460 (in Districts 1, 2 and 3);

- $9,536 (in District 4);

- $40,070 (in District 6);

- $114,097 (in District 7); and

- $253,163 total for all districts.

Thirteen percent or 568 of all LIHEAP households in the program area use electric heat. The amount paid by homes with electric heat was as follows:

- $30,846 (in District’s 1, 2 and 3);

- $25,421 (in District 4);

- $22,596 (in District 6);

- $144,008 (in District 7); and

- $222,871 total for all districts.

The Number and Percent of Utility Shutoffs Among Low-Income Consumers

In 1998, Montana Dakota Utilities (MDU) disconnected 1307 low-income consumers for non-payment.  This represented 2 percent of its total Montana customer base.  In 1998, Montana Power Company/NorthWestern Energy (MPC/NWE) disconnected 3350 low-income consumers for non-payment.  This represented 2 percent of its total Montana customer base.  MPC/NWE and MDU serve approximately 59 percent of Montana’s LIHEAP caseload.  Unlike Montana’s unregulated cooperatives and independent fuel vendors, MDU and MPC are subject to Public Service Commission imposed moratorium on winter shutoffs.

Climatic Conditions

Climatic conditions vary widely from region to region in Montana.  The eastern half of Montana, which was included in the service area of the Montana REACH program, consists of vast areas of prairie, farm and ranch land.  Annual precipitation ranges from 11 to 17 inches in the program area.  Average 12 month temperature ranges from 42 in North Central Montana (District 4) to 46 in the easternmost districts (Districts 1, 2 and 3).

Unemployment Statistics for the Area

In general, for the 31-county area, unemployment rates increased steadily from 1998 to 1999.  In eastern Montana unemployment equaled the statewide average of 5.6% in March of 1999.  The prosperity of the program area, highly dependent upon agriculture, reflects the downturn in that sector of the economy.  The Montana REACH region contained five tribal reservations, the Crow, Fort Belknap Reservation, Fort Peck Reservation, Northern Cheyenne and the Rocky Boy Reservation.  The average unemployment of the five reservations is 71%.

Price of Fuels and the Demand Management Services Offered by Local Utilities at Start of REACH

The price of fuels was as follows:

Montana Power Company/NWE Electricity			$0.072 per KWH

Montana Dakota Utilities Electricity					$0.072 per KWH

Other Electric Providers								$0.06472 per KWH

Oil														$91.8 cents per gallon

Propane (winter rates)									$1.29 per gallon

Propane (summer rates)								$0.69 per gallon

Natural Gas											$5.047 per MCF

Montana Power Company/NWE Natural Gas			$4.9393 per MCF

Montana Dakota Utilities Natural Gas					$5.35 per Decatherm

Wood													$65.00 per cord

Coal													$65.00 per ton

The winter and summer rates are listed for propane to illustrate the fuel cost savings potential the LIHEAP consumers have by purchasing propane in the summer months when prices are at their lowest.  The Montana REACH program gave clients this option by providing participants ownership of larger propane tanks.

Only one electric cooperative, Yellowstone Valley Electric in District 7 REACH region, offers incentives for switching to heat pumps or performing energy saving measures.  The cooperative offers a $1000 rebate on geothermal heat pumps, a $750 rebate on air source heat pumps and free 40 to 70 gallon water heaters with high demand shut off switches.  They also offered a 5 percent loan on approved credit to help finance these retrofits.  According to their management, they were willing to work with other programs to help fund these retrofits.  No other utility company or fuel vendor in the program area provides such an option which is one reason this portion of the state was targeted for this program.

# III.  Program Design Framework: Interventions, Outcomes and Goals

Over the course of the Montana REACH program period at least 600 LIHEAP households were to be selected by the four (4) Community Action Agencies listed above.  They participated in the following activities which were to be provided in addition to and in coordination with regular LIHEAP benefit payments and emergency services.  No regulated utility covered by the program was required to act in a manner that is inconsistent with applicable regulatory requirements.

The four (4) Community Action Agencies listed previously provided the services described below. In doing so they solicited and were responsive to the views of individuals who are financially eligible for benefits and services under the Montana REACH program.

# Intervention

Initial Household Assessment

The initial assessment performed on all dwellings included a client education questionnaire, diagnostic testing and inspection of combustion heating devices, a heating system retrofit analysis, and an inspection to identify necessary energy related health and safety and minor home repairs and assess the need for smoke and carbon monoxide detectors.

The client education questionnaire (Appendix A) consisted of a series of appliance usage and building characteristics questions designed to build an energy consumption profile for each dwelling.  This information was utilized to structure energy conservation counseling which was part of the energy education phase of the Montana REACH program.  To reinforce household specific energy conservation counseling, a quarterly newsletter containing follow-up energy conservation tips and reminders was mailed to program participants throughout the 36-month duration of the program (Appendix B).

An analysis was performed to determine the cost effectiveness of switching water and/or space heat devices in eligible dwellings.  The analysis performed on each dwelling utilizing the Montana REACH Program – Cost Effectiveness Analysis, a computerized audit, to analyze heating system efficiencies and the cost effectiveness of upgrades (Appendix C).  Space and/or water heating devices were retrofitted in instances where doing so was cost effective by virtue of demonstrating a savings to investment ratio of at least 1.0.  In at least half of all rental situations, landlords were required to contribute 25 percent of costs associated with respective heating system retrofits.  Fuel vendors/utility companies supplying fuel to retrofitted heating systems were also asked to contribute or provide discounts and fee waivers equal to 25 percent of all costs associated with retrofits.

In instances where retrofits were not cost effective, existing heating appliances were to be cleaned, tested, checked for safety problems and repaired by certified heating system technicians utilizing state of the art diagnostic equipment, which followed procedures, contained in the attached Heating Worksheet (Appendix D).  Propane and fuel oil tanks were purchased, when applicable, to provide LIHEAP households a choice in fuel vendors and the opportunity to purchase these fuels at low summer prices.

Mercury thermostats replaced in the course of performing retrofits and repairs were returned (at no cost to the REACH program) to manufacturers participating in the Mercury Thermostat Reduction and Recycling Program sponsored by the Thermostat Recycling Corporation as a means of reducing mercury levels in landfills.  Where appropriate programmable “night set-back” thermostats wer installed.

In addition to the above activities, inspections were performed on each dwelling by a certified energy auditor to determine whether there existed opportunities to provide health and safety measures and perform cost-effective energy conservation related home repairs. The scope of the inspection included examination of the dwelling envelope and an assessment of existing carbon monoxide and smoke detectors.

# Immediate Changes/Outcomes

Client Education

Designing an energy consumption profiles for program participants resulted in implementation of household specific energy conservation counseling and identification of unique opportunities to influence energy usage behavior.  Information obtained from energy consumption profiles and energy usage counseling was incorporated in newsletters to reinforce and sustain behavioral changes in household energy usage.  Client education was intended to increase energy efficiency, lower out-of-pocket heating costs and improve safety and comfort levels in LIHEAP households.

Heating System Retrofits

Heating system retrofit analyses resulted in the identification of opportunities and implementation of cost-effective activities intended to increase energy efficiency, lower out-of-pocket home heating costs and increase comfort levels in households through the replacement of inefficient heating systems.

Existing Heating System Testing, Safety Inspection and Repair

Heating system testing and safety inspections resulted in the identification and installation of heating system repairs and rectification of life threatening health and safety conditions in households.  Heating system repairs also contributed to an increase in heating efficiency, lower out of pocket heating costs and improved comfort levels and safety conditions in households.

Energy Conservation and Health and Safety Related Minor Home Repair Assessment

Home repair assessments resulted in minor home repairs intended to protect existing energy conservation measures and reduce or eliminate the need for costly future replacement.   Health and safety related minor home repairs, included the installation of no more than one (1) carbon monoxide detector and one (1) smoke detector per dwelling to improve safety conditions in homes.  Energy conservation and health and safety related repairs resulted in increased energy efficiency, lower out-of-pocket heating costs and improved safety and comfort levels in LIHEAP households.

# Intermediate Changes/Outcomes

Client Education

Over the 36-month program period, 600 households were to receive client education counseling based upon their energy usage profiles.  All REACH participant households also received newsletters intended to reinforce and sustain energy usage behavioral changes.   Client education activities were to be performed at an average cost of $250 per participating household.

Heating System Retrofits

Over the 36 month program period, 325 heating systems (space and/or water) were to be cost effectively retrofitted at an average cost to the REACH program of $2,696 per dwelling.  In at least half of all rental situations, landlords were required to pay 25 percent of the costs of retrofitting heating systems (space and/or water).   Landlord contributions were intended to increase the minimum number of households participating in the REACH program at a rate of one (1) additional household per $2,125 in landlord contributions.  Fuel vendors were asked to provide fee waivers, discounts and co-funding equal to 25 percent of the costs of retrofitting heating systems (space and/or water).  Vendor co-funding was intended to increase the minimum number of households participating in the REACH program at a rate of one (1) additional household per $2,125 in vendor co-funding.  Heating system retrofits performed under this proposal were to result in discounted (at a rate of 4.7 percent) savings to participant households (over the program lifetime of each retrofit (20 years for furnaces and 13 years for domestic water heaters)) equal to or greater than the total retrofit cost to the REACH program.

Existing Heating System Testing, Safety Inspection and Repair

Over the 36 month program period, 275 existing heating systems (space and/or water) were to be inspected, tested, cleaned and repaired at an average cost of $250.18 per dwelling.

Energy Conservation and Health and Safety Related Minor Home Repairs

Over the 36-month program period, 600 households were to receive energy conservation and health and safety related minor home repair at an average cost not to exceed $300 per dwelling.   100 percent of participating households utilizing combustion heating or cooking devices were to have installed, digital read-out carbon monoxide detectors and receive instruction on the use and operation of same.  100 percent of participating households that lack working smoke detectors were to have one (1) installed and receive instruction on the use and operation of it.  Costs associated with smoke and carbon monoxide detectors are included in the $300 per dwelling average noted above.

# Achievement of Overall Program Goals

The above described REACH activities and outcomes coupled with existing LIHEAP heating assistance benefits were intended to contribute to the overall goal of the REACH program which was to ensure that low-income families have the resources necessary to live in decency and health by:

- Ensuring the energy burdens of low income Montanans are no higher as a percentage of annual income than the average for all Montanans (4.1% of household income).

- Ensuring that dwellings occupied by low-income Montanans are free of energy-related health and safety hazards.

- Requiring landlords and encouraging fuel vendors to participate financially in activities intended to increase low-income families’ ability to pay energy costs in a timely manner.

- Improving low-income Montanans ability to regularly pay energy costs.

- Eliminating homelessness due to high-energy costs and/or the presence of energy-related health and safety hazards.

- Providing low-income households, especially Montanans welfare reform participants, more disposable income to satisfy basic needs necessary to achieve self-sufficiency.

- Protecting the integrity of existing energy conservation measures in low-income dwellings and reducing or eliminating the need for future energy conservation investment.

- Positioning low-income Montana families to take advantage of customer choice opportunities arising as a result of electric and natural gas industry restructuring or ownership of fuel oil or propane tanks.

- Encouraging fuel vendors and utility companies to satisfy their respective low-income uniform systems benefit program obligations (established in Montana law as a percentage of each companies 1995 gross operating revenues) through future replication of the activities/interventions contained in this proposal.

# Work Plan

| Intervention |  | Quantitative Outcome (# of Households) |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Program Activities | Description | Year 1 | Year 2 | Year 3 | Total |
| Initial Household Assessment | The initial assessment performed on all dwellings shall include a client education questionnaire, diagnostic testing and inspection of combustion heating devices, a heating system retrofit analysis, and inspection to identify necessary energy related health and safety and minor home repairs and assess the need for smoke and carbon monoxide detectors. | 176 | 212 | 212 | 600 |
| Client Education | Energy consumption profiles for participants will be conducted. Each household will receive specific energy conservation counseling and identification of unique opportunities to influence energy usage behavior. Information obtained from energy consumption profiles and energy usage counseling will be incorporated in quarterly newsletters whose purpose shall be to reinforce and sustain behavioral changes in household energy usage. | 176 | 212 | 212 | 600 |
| Heating System Retrofits | Heating system retrofit analyses will be conducted. Cost-effective activities intended to increase energy efficiency, lower out-of-pocket home heating costs and increase comfort levels in LIHEAP households will be implemented. | 93 | 116 | 116 | 325 |
| Heating System Test and Repair | Heating system testing and safety inspections will identify threatening health and safety conditions requiring repairs. Heating system repairs will be conducted. Heating system repairs will also result in increased heating efficiency, lower out of pocket heating costs and improved comfort levels and safety conditions in LIHEAP households. | 93 | 96 | 96 | 275 |
| Health and Safety Minor Home Repair | Assessments and minor home repairs intended to protect existing energy conservation measures and reduce or eliminate the need for costly future replacement will be conducted. Health and safety related minor home repairs, including installation of no more than one (1) carbon monoxide detector and one (1) smoke detector per dwelling, will improve safety conditions. | 176 | 212 | 212 | 600 |

# Program Logic Model

| STATE / AGENCY: Montana Department of Public Health and Human Services (DPHHS), Intergovernmental Human Services Bureau(IHSB) |  | CONTACT: State: Kane Quenemoen (406) 447-4267 Evaluators: Mike Vogel/Chris Mee (406) 994-3451 |  |  |
| --- | --- | --- | --- | --- |
| PROGRAM: MONTANA REACH PROGRAM |  |  |  |  |
| ESTIMATED PROGRAM START DATE: 01/01/2000 |  |  |  |  |
| ESTIMATED PROGRAM COMPLETION DATE: 01/01/2003 |  |  |  |  |
| PROGRAM GOAL: To ensure participants have the resources to live in dignity and health. |  |  |  |  |
| OBJECTIVES | INDICATORS |  | MEANS OF VERIFICATION | ASSUMPTIONS |
| IMMEDIATE OUTCOMES OR OUTPUTS: |  |  |  |  |
| Number of and Cost per heating systems (both Water and Space heat) retrofitted per CBO each year | -# of heating system retrofits. -avg. cost per retrofit. |  | -energy audit from HRDC’s | -the dwelling has a heating system which qualifies for a retrofit |
| Number of and Cost of Heating system diagnostic test, inspection, and repair per CBO year. | -# of heating system diagnostic tests. -avg. cost per diagnostic test |  | -energy audit from HRDC’s | -the dwelling has a heating system which needs maintenance. |
| Households of participants are inspected and energy efficient | -#completions |  | -post audit documentation and verification of installation | -the dwelling is in need of energy efficient measures. |
| INTERMEDIATE OUTCOMES OR PROGRAM PURPOSE: |  |  |  |  |
| Improve Low-Income Montanans = ability to regularly pay energy cost; | % MT LIEAP homes in arrears % of all MT homes in arrears % REACH recipients in arrears |  | -public service Comm. -participant surveys. -utility company reports. | -arrearage rate correlates with ability to pay |
| OBJECTIVES | INDICATORS |  | MEANS OF VERIFICATION | ASSUMPTIONS |
| Providing low-income households, especially Montana=s welfare reform participants, more disposable income to satisfy basic needs necessary to achieve self-sufficiency; | % reduction in energy consumption |  | -utility consumption data. | -money households save on energy will be used to satisfy basic needs. |
| Eliminating homelessness due to high energy costs and presence of energy related health and safety hazards; | #/% of REACH recipients reporting homelessness due to high energy costs or health and safety hazards. |  | -participant surveys. | -other influences on behavior such as environment, economic or social circumstances do not get worse |
| Ensuring that dwellings occupied by low-income Montanans are free of energy related health and safety hazards; | #/% of REACH recipients reporting presence of energy related health and safety hazards after work is done. |  | -audits from HRDC’s Survey | -households are able to identify and describe health and safety hazards if they exist. |
| Protect the integrity of existing energy conservation measures in low-income dwellings and reducing or eliminating the need for future energy conservation investments. | #/% of REACH homes in which energy conservation measures protected. #/% of REACH homes reporting no need for future energy conservation measures. |  | -audits from HRDC’s Survey | -the residence is not in disrepair. |
| Requiring landlords and encouraging fuel vendors to participate financially in activities intended to increase low-income family’s ability to pay energy costs. | -landlord and fuel vendor contribution as a % of all expenditures and relative to stated goals. |  | -audits from HRDC’s | -landlords are willing to participate and contribute. |
| OBJECTIVES | INDICATORS |  | MEANS OF VERIFICATION | ASSUMPTIONS |
| Participants achieve energy savings, or reduction in energy burden. | #/% REACH participant achieving lower energy consumption. |  | -pre and post consumption on a sample of metered recipient. | -other influences on behavior such as environment, dwelling characteristics, economic or social circumstances do not change -metered homes also representative of homes heated with storable fuels |
| Positioning participants with the ability to take advantage of lower cost propane or fuel oil, during the off season and use the money that would have been used to pay rent on the tank to purchase fuel, by purchasing fuel tanks | #/% REACH participant achieving lower energy consumption. |  | -participants survey | -participants are willing to take advantage of lower cost propane or fuel oil early in the heating season. |
| ACTIVITIES: Housing improvements: - Audit household conditions. - Weatherize homes as needed using other funds - Health & safety household improvements - Heating system conversions, retrofits, and clean and tune. | Hous |  | -budget records or audit reports. | -low-income households can be weatherized and made energy efficient. |
| Evaluation and Monitoring: - Collect baseline data on participant’s energy practices. - Collect follow-up data during and after participation - Install measures - Monitor performance measures. |  |  | -data base, historical and updated. | -historical data on energy utilization is available from energy companies: -energy data is available in useable formats. |

# Program Changes and Modifications

During the program period only one major program change/modification was necessary.  It entailed a funding reallocation change which occurred through the determination of a sub-grantees inability to spend its allotment.  The funds were redistributed to other sub-grantees for use in their REACH programs.  This did not affect the outcome of the program since the money allocation was adjusted to continue the program at a higher number of completions at these agencies and diminishing the level and allocations of completions the other.

# IV. Evaluation Methodology

Overview

An important component of the REACH program was the evaluation of the activities carried out with REACH funds and their efficacy in achieving goals related to reducing participant home energy costs and increasing the ability of participants to meet such costs independent of payment subsidies.   Accordingly, the grantee contracted with the Montana State University (MSU) Extension Service for the duration of the program to perform an overall process and outcome evaluation and provide the grantee, CBOs and other interested parties summary information and continual feedback necessary to ensure the most efficient and effective implementation of all program activities.  The lead evaluator representing MSU was Mr. Christopher L. Mee Weatherization Technical Specialist under the direction of Dr. Michael P. Vogel, Professor and Housing and Residential Energy Specialist.

As noted above, the premise from which all of the activities and interventions of this program were derived is that low-income Montanans pay a disproportionate amount of their incomes toward home energy costs and live disproportionately in substandard and unsafe housing.   Through implementation of the REACH activities, it was the goal of the program to ensure that participating families have the resources necessary to live in decency and health by:

- Ensuring their energy burden is no higher as a percentage of annual income than the average for all Montanans (4.1% of household income).

- Ensuring their home is now free of energy-related health and safety hazards.

- Encouraging landlords and fuel vendors to participate financially in activities intended to increase their ability to pay energy costs in a timely manner.

- Improving their ability to regularly pay energy costs.

- Eliminating the prospect of homelessness due to high-energy costs and/or the presence of energy-related health and safety hazards.

- Providing them, especially those who are participating in Montanans welfare reform program, more disposable income to satisfy basic needs necessary to achieve self-sufficiency.

- Protecting the integrity of existing energy conservation measures in their homes and reducing or eliminating the need for future energy conservation investment.

- Positioning participating families to take advantage of customer choice opportunities arising as a result of propane or fuel oil tank ownership and/or electric and natural gas industry restructuring.

- Encouraging participants fuel vendors and utility companies to satisfy their respective low-income uniform systems benefit programs obligations (established in Montana law as a percentage of each company’s 1995 gross operating revenues) through co-funding REACH activities and future replication of the activities/interventions contained in this proposal.

To achieve the overall goal and sub-elements of the program, dwellings occupied by LIHEAP households (those with the highest documented energy needs) were assessed and provided energy conservation and health and safety related minor home repairs and client education.  Approximately 325 of the 600 participating LIHEAP households were, as a result of receiving a heating system retrofit energy audit, switched to a more cost effective heating system and/or heating fuel source.  The heating systems of all other participant households were tested, inspected and if necessary repaired.

Data Collection Procedures

Data was collected throughout the program period by the use of the Client Education Tool (CET) REACH Evaluation page, and Energy Consumption pre and post page.  The data in the CET was entered by each CBO and delivered through disk media or electronic mail.  After the data was collected it was then transferred to a database, which in turn was used for verification and analyzes through tables, queries and reports.   All process and outcome data was derived from the database.

# V. Process Evaluation Findings

- The number of and cost per heating system (for both water and space heat) retrofitted each year of the program

- The number of and cost per heating system diagnostic test, inspection and repair was $29.56 based on 268 participants from all CBO’s and a grand total of $7,922.88 for all heating system diagnostic tests, inspections and repairs

- The number of dwellings impacted by Minor Home Repair was 171 with an average cost of $302 per dwelling.

- The number of dwellings impacted by protecting energy conservation measures was 3 with and average cost of $280 per dwelling.

- The number of dwellings impacted by health and safety was 74 with an average cost of $819 per dwelling.

- The number of dwellings impacted by client education was 452 with an average cost of $95.85 per dwelling.

The total cost for all Health and Safety, Energy Conservation, Minor Home Repairs and Client Education was $152,427

Agency Survey Information

- The adequacy of annual CBO budget allocations relative to completion goals in all program elements.

- At the beginning of the grant cycle the fund allocations were allotted based on a subgrantee survey conducted by the DPHHS.  After the grant was in full swing the budget allocation was adjusted based on an individual subgrantee assessment. All agencies reported that the Allocation was adequate.

- Effectiveness of proposed participant selection methodology in ensuring households with the highest energy needs receive assistance under the program;

- Through the utilization of a priority list generated by DPHHS, each agency was able to determine the homes with the highest energy need, which were typically electric and propane, and then proceeded with REACH activities.  In general homes with the highest energy need were served first and only on rare occasions were homes that had lower energy needs served by the program.

- Effectiveness of heating system diagnostic equipment and Heating Worksheet procedures in identifying and addressing heating system health, safety and efficiency issues;

- The heating worksheet was used successfully to help keep heating technicians on track while analyzing a heating system.  Health, safety, and efficiency issues were easily identified by the use of the worksheet.  It served as a valuable tool in keeping record of these issues so they could be taken care of appropriately.  The utilization of diagnostic tools and equipment in conjunction with the heating worksheet was valuable in documenting actual levels of carbon monoxide and efficiency of heating systems.

- Adequacy and ease of use of the computerized retrofit audit utilized to assess the cost effectiveness of heating system retrofits;

- The retrofit audit uses a cost per Btu analysis to determine a savings to investment ratio which adequately showed the cost effectiveness of a fuel switching retrofit.  It was well utilized by all agencies and through this audit many heating systems were retrofitted for efficiency.

- Effectiveness of measures utilized by CBOs and the grantee to ensure REACH program quality control and financial accountability;

- Each sub-grantee followed a priority list provided by the State of Montana where home were prioritized on a ratio of heating costs to client income.  Typically, they worked mostly on the higher cost fuels such as electricity and propane and seldom was a lower energy fuel home completed.

- Adequacy and understandability of client education and educational materials intended to encourage fuel vendor and landlord financial contributions

- After being adequately trained on the uses of the Client Education Spreadsheet, the client education specialist/auditors were able to show clients where their energy dollars were going and by utilizing the Power Bill energy tip brochures, provided by Montana State University Extension Service, where able to further express ways to save energy.

- Number of utility companies and fuel vendor’s adopting/co-funding program activities to satisfy their respective low-income uniform system benefits program requirements.

- Through the course of the REACH program no new fuel vendor’s or utility company’s adopted/co-funded programs then before the program.

Client Summary Data

- The average energy burden for all REACH participants for 2001 was 8.35%.

- The mean annual income across all agencies and participants was $9,812.11

- The type of dwellings occupied were, 
227 Mobile homes
314 Single family dwellings
10 Multi Family dwellings

- The mean number of occupants per REACH participant household was 2.75,

- The mean age of occupants was 59.75 years old,

- The total costs and numbers of programmable thermostats was 6 at a total cost of $295.00,

- The total cost of replacement fuel tanks was $271,002.  There were 239 purchased at an average cost of $1,134,

- The total cost of smoke alarms installed for all participants was $3230.69.  There were 200 purchased at an average cost of $16.15,

- The total cost of carbon monoxide detectors was $12,001.04.  There were 288 detectors installed at an average cost of $41.67,

# VI. Outcome Evaluation Findings

Energy Cost Reductions

The Annual energy cost (normalized to reflect actual heating degree days) of participant households during the year prior to participating in REACH was $1001.00.  During the year immediately after receiving REACH services, the average energy cost was $932.00.  This represents an annual savings of 7% for REACH households.  The average energy burden of all LIHEAP recipients for 2001 and 2002 was 9.1 %.  The Average burden for all REACH participants for 2001 was 8.35%.

| Agency | Average Household Income | Pre- WX Energy Consumption |  | Pre- WX Energy Use as % of Income | Post-WX Energy Consumption | Pre- WX Energy Use as % of Income | $ Consumption Change | % Change |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Action for Eastern MT | $10,217.55 |  | $1,031.00 | 10.1% | $951.00 | 9.3% | -$80.0 | -7.8% |
| District 4 HRDC | $16,280.75 |  | $922.00 | 5.7% | $817.00 | 5.0% | -$105.0 | -11.4% |
| District 6 HRDC | $10,797.80 |  | $992.00 | 9.2% | $910.00 | 8.4% | -$82.0 | -8.3% |
| District 7 HRDC | $11,744.40 |  | $1,001.75 | 8.5% | $932.00 | 7.9% | -$69.8 | -7.0% |

Utility and Fuel Bill Arrearage

The following chart shows the frequency and amount of utility company/fuel vendor arrearages among a select number of participants in the program who were part of the outcome energy burden analysis above.  Base on account number these numbers were the totals acquired through the utility company assistance.

| Northwestern Energy Clients |  |  |  |
| --- | --- | --- | --- |
| After REACh Services |  |  |  |
| Sample Size = 23 |  |  |  |
| Description | Number | Percentage |  |
| Arrears |  |  |  |
| Between 0-2 months of arrears out of 12 month period | 13 | 56.5% |  |
| More than 2 months of arrears out of 12 month period | 10 | .43.5 |  |
| Regular Payments |  |  |  |
| Paid something every month | 18 | 78.3% |  |
| Made sporadic payments during 12 month period | 3 | 13.0% |  |
| Made no payments during 12 month period | 5 | 8.7% |  |
| MDU Account after REACh |  |  |  |
| # of Occurrences for 12 month Period |  |  |  |
| Sample size =12 |  |  |  |

| Arrears |  |  |
| --- | --- | --- |
| Between 0-2 months of arrears out of 12 month period | 6 | 50% |
| More than 2 months of arrears out of 12 month period | 4 | 33% |
| Regular Payments |  |  |
| Paid something every month | 6 | 50% |

Miscellaneous Findings

- Total utility company/fuel vendor contributions toward program activities intended to reduce energy burdens of eligible households:  $23,896.

- Total landlord contributions toward program activities intended to reduce energy burdens of eligible households:  $29,542.

- Percent of natural gas, electricity, fuel oil and propane fueled participant households aware of and taking advantage of customer choice of fuel suppliers:

From the onset of the REACH program the ability of clients to choice their fuel supplier was limited to those who used propane as a source of heat.  As a result of the propane tank purchasing for these clients it has been determined that 239 propane clients now have the ability to take advantage of customer choice in fuel supplies.  This has allowed for purchasing propane at substantially lower prices at the beginning of the heating season as well as the ability to shop around for the lowest price when the heating season is in full swing and propane prices have increased to meet the demand.

- Total avoided cost of replacement energy measures as a result of minor home repairs:

Though it is hard to estimate a dollar figure here, District 7 indicated that there was approximately $3500.00 of avoided cost for there agency.  There were situations that other agencies remarked concerning these measures such as replacing floors in mobile home water heater compartments which certainly would be avoided costs of future minor home repair.

- Number of Montana utility companies and fuel vendors replicating program activities to meet their respective USBC guidelines:

MDU, MPC, Energy West-Great Falls Gas, Hill County Electric, Big Flat Electric, Lincoln Electric and all Bonneville Power Company electric cooperatives contribute/sponsor low income weatherization activities in the state.  Collectively they serve over 70 percent of Montana’s residential customers.

- Frequency of heating system condemnations among  LIHEAP recipients in general and among REACH program participants specifically:

105 REACH Program Participants had Heating System condemnations.

###### Note : Need LIHEAP condemnations

- Frequency of Utility Termination Notices Among LIHEAP and REACH participants:
LIEAP Recipients	5.860%
REACH Recipients	4.936%

- Frequency of Eviction Notices Among:

LIEAP Recipients	0.378%
REACH Recipients	0.000%

# VII. Client Survey

Overview

At the conclusion of the Montana REACH program, participants were asked to complete a questionnaire about their REACH experience. The overwhelming consensus of 126 participants that returned their survey was that the REACH program was extremely beneficial to them and to their families. The participant’s comments reflect the many ways in which the Montana REACH program has had a positive impact on their household environment and their ability to better manage their energy resources.

Client Survey Outcomes

| - Before receiving REACH/Weatherization services in my home I was able to pay my energy bill in full every month; Always 25 Participants 19.84% Most of the Time 41 Participants 32.54% Some of the Time 20 Participants 15.87% Rarely 36 Participants 28.57% No Answer 4 Participants 3.17% | - After receiving REACH/ Weatherization services in my home I was able to pay my energy bill in full every month: Always 67 Participants 53.17% Most of the Time 38 Participants 30.16% Some of the Time 2 Participants 1.59% Rarely 12 Participants 9.52% No Answer 7 Participants 5.56% |
| --- | --- |

| - Before REACH/ Weatherization services were conducted on your home, how often did you worry about having to move from your home because of High Energy Cost: Often 20 Participants 15.87% Some of the Time 31 Participants 24.60% Rarely 27 Participants 21.43% Never: 41 Participants 32.54% No Answer 7 Participants 5.56% | - After REACH/ Weatherization services were conducted in your home, how often did you worry about having to move from your home because of High Energy Cost: Often 2 Participants 1.59% Some of the Time 22 Participants 17.46% Rarely 23 Participants 18.25% Never 73 Participants 57.94% No Answer 6 Participants 4.76% |
| --- | --- |

| - Before receiving REACH/ Weatherization services in your home, how often did you worry about having to leave your home because of energy related health and safety issues: (Examples of which would include: Carbon Monoxide, Failing Roof, Broken window) Often 19 Participants 15.08% Some of the Time 33 Participants 26.19% Rarely 22 Participants 17.46% Never 47 Participants 37.30% No Answer 5 Participants 3.97% | - After receiving REACH/ Weatherization services in your home, how often did you worry about having to leave your home because of Energy Related Health and Safety Issues: (Examples of which would include: Carbon Monoxide, Failing Roof, Broken window) Often 4 Participants 3.17% Some of the Time 9 Participants 7.14% Rarely 27 Participants 21.43% Never 80 Participants 63.49% No Answer 6 Participants 4.76% |
| --- | --- |

| - Before having REACH/ Weatherization services completed on your home did you feel your home was free of Energy Related health and safety hazards? All of the time 60 Participants 47.62% Most of the time 33 Participants 26.19% Some of the time 19 Participants 15.08% Very Concerned about potential health and safety problems 11 Participants 8.73% NO Answer 3 Participants 2.38% | - After having REACH/ Weatherization services completed on your home did you feel your home was free of Energy Related health and safety hazards? All of the time 24 Participants 19.05% Most of the time 36 Participants 28.57% Some of the time 30 Participants 23.81% Still Concerned about potential health and safety problems 32 Participants 25.4% No Answer 4 Participants 3.17% |
| --- | --- |

- A. Did the ability to purchase lower cost fuel throughout the year because you owned your own propane tank, affect your overall fuel cost for the year: (If your home is not heated with propane, skip to next question.) More than I expected 29 Participants 23.02% Somewhat 8 Participants 8.73% Less than I expected 1 Participants .79% None 19 Participants 15.08% NO Answer 66 Participants 52.38% B. Do you feel your fuel cost went up or down? UP 9 Participants 7.14% DOWN 37 Participants 29.37% Stayed the Same 2 Participants 1.59% No Answer 77 Participants 61.11%

- As a result of REACH/ Weatherization services being performed in my home, my home is comfortable and livable: More than expected 91 Participants 72.22% Did not change 18 Participants 14.29% Less than expected 7 Participants 5.56% No Answer 10 Participants 7.94%

- Did the Client education tips that you received through the REACH/WX Program help you to understand your energy usage: A lot 69 Participants 54.76% Somewhat 33 Participants 26.19% Very Little 10 Participants 7.94% Not at all 5 Participants 3.97% No Answer 9 Participants 7.14%

- Did the Client education tips that you received through the REACH/WX Program help you to lower energy usage: A lot 51 Participants 40.48% Somewhat 47 Participants 37.30% Very Little 14 Participants 11.11% Not at all 6 Participants 4.76% No Answer 8 Participants 6.35%

# Appendix

- client education questionnaire (SEE ATTACHED)

- REACH Newsletters (SEE ATTACHED)

- REACH Switch AUDIT (SEE ATTACHED)

- Montana HEATING Worksheet (SEE ATTACHED)

- client Survey (SEE ATTACHED)